## Notes
Sr. No. | Section | Module | Error / Requirement
1 | UI + feature Testing | Super Admin | login issues - logins stored (unencrypted)
2 | UI + feature Testing | Super Admin | what if multiple wants to check + different schools or for ticket solving.
3 | UI + feature Testing | Dashboard | what to show
4 | UI + feature Testing | Dashboard | Students info required?
5 | UI + feature Testing | Dashboard | Total schools present
6 | UI + feature Testing | Dashboard | Total Users logged in
7 | UI + feature Testing | Dashboard | Total Active Users
8 | UI + feature Testing | Schools | Register -> mail sent
9 | UI + feature Testing | Schools present | Info -> Total Students Present -> Contact -> Delete deactivate
10 | UI + feature Testing | Features | Remove
11 | UI + feature Testing | Admin Details | Reset password
12 | UI + feature Testing | Enrollment | Count of enrolled students per class.
13 | UI + feature Testing | Student Directory | Show Students Data?
14 | UI + feature Testing | Content Portal | Global Quest Bank [Remove]
15 | UI + feature Testing | Content Portal | PYQ's logic
16 | UI + feature Testing | Content Portal | Book library/Textbook upload/PYQ's/Subjects
17 | UI + feature Testing | Content Portal | Remove the yellow Error line while uploading 2 PDFs
18 | UI + feature Testing | Content Portal | Diff filters for PYQ's upload
19 | UI + feature Testing | Error messages | no chp detected
20 | UI + feature Testing | AI Console | AI Vlm model changing
21 | UI + feature Testing | AI Console | features Activate/deactive
22 | UI + feature Testing | AI Console | usage visibility
23 | UI + feature Testing | AI Console | API hitting
24 | UI + feature Testing | AI Console | AI calls (month, day)
25 | UI + feature Testing | Support Tickets | View Raised Tickets By - School-Adm / Teachers
26 | UI + feature Testing | Support Tickets | Solving Status Update
27 | UI + feature Testing | Support Tickets | Categorise the issues
28 | UI + feature Testing | Support Tickets | Sync the Ticket updation status to SA + teacher properly Per School.
29 | UI + feature Testing | Support Tickets | If same Issue -> Bulk updation of status
30 | UI + feature Testing | Audit logs | Types of logs
31 | UI + feature Testing | Audit logs | Adding / Active / deletion of schools
32 | UI + feature Testing | Audit logs | Mails
33 | UI + feature Testing |  | Same login's
34 | UI + feature Testing |  | Adding Teachers&Students Credentials - by SchoolAdmin
35 | UI | UI | remove unwanted texts like K-12 Portal
36 | UI | UI | Good product logo + Name Branding
37 | UI | UI | Right side [U] [Remove]
38 | UI | UI | Good Profile + Setting option in one like small dropdown
39 | UI | UI | Good working Analysis of Schools + users (Overview)
40 | UI | UI | AI Console -> Improve UI
41 | UI | UI | Support Ticket -> UI -> Good View
42 | School Admin | Profile / Setting | Profile / Setting / Reset Password
43 | School Admin |  | Dashboard
44 | School Admin | Dashboard | Total students / Teachers -> Active / logged in view
45 | School Admin | Dashboard | View suggestion - No fake data's
46 | School Admin | Dashboard | Show classes having sessions
47 | School Admin |  | Classes + Sections
48 | School Admin | Classes + Sections | Add whole table - Adding class/section - Assigning Teacher for class
49 | School Admin |  | Students
50 | School Admin | Students | Create good full view table with existing features/filter
51 | School Admin | Students | Import section (Bulk for multiple class)
52 | School Admin | Students | Delete students / deactive / left school
53 | School Admin | Students | New 1st Batch + Pass outs Students
54 | School Admin |  | Teachers
55 | School Admin | Teachers | Whole Table full view
56 | School Admin | Teachers | Importing Teachers (Bulk)
57 | School Admin | Teachers | Add more filters
58 | School Admin | Labs | Labs [Remove] Periods
59 | School Admin | Timetable | Timetable Import [format] [yearly] [weekly]
60 | School Admin | Timetable | might change in Timetable (Teacher not available)
61 | School Admin | General | remove -No showing unwanted errors only if necessary
62 | School Admin | Content Library | Content Library
63 | School Admin | Content Library | Content Library
64 | School Admin | Content Library | Give limit max 3 per class
65 | School Admin | Lab Incharge | Lab Incharge [Remove]
66 | School Admin | Feature Toggle | Feature Toggle remove
67 | School Admin | School Branding | School Branding -remove [Add to Profile/Setting]
68 | School Admin | Principal Report | Principal Report remove
69 | School Admin | Promotion Wizard | Promotion wizard remove
70 | School Admin | Support Ticket | Support Ticket
71 | School Admin | Support Ticket | Add categories
72 | School Admin | Support Ticket | Remove 'Status' from SupportTickets
73 | UI | Dashboard | Dashboard -> More Impression
74 | UI | Dashboard | Real Data Only
75 | UI | Settings | Add Setting - Profile + Password
76 | UI | Sidebar | Left Sidebar (Scroll Bar)
77 | UI | Sidebar | Remove Right side [O]
78 | UI | Classes & Section | Classes & Section
79 | UI | Students | Good Table with filters
80 | UI |  | Students
81 | UI | Students | the Poster (Reduce size)
82 | UI | Students | make Table Big
83 | UI | Students | Improve Import roster
84 | UI |  | Teachers
85 | UI | Teachers | Reduce Poster Size (Table Big)
86 | UI |  | Improve 'Import faculty' pop-up
87 | UI | Teachers | write the format of uploading
88 | UI |  | Labs
89 | UI | Labs | Remove labs
90 | UI |  | Timetable
91 | UI | Timetable | Improve view
92 | UI | Timetable | Improve Import
93 | UI | Timetable | Fix error showing
94 | UI | Content Library | Content Library
95 | UI | Content Library | Small Poster
96 | UI | Content Library | Remove Generate Questions
97 | Teacher | Dashboard | Show a short view of the Timetable on the Dashboard.
98 | Teacher | Dashboard | Show more useful analytics on the Dashboard.
99 | Teacher | Live Sessions | Remove Live Sessions.
100 | Teacher | Timetable | Change/improve the Timetable view; the current view is not efficient.
101 | Teacher | Students | Show only students from the particular class assigned to the teacher?
102 | Teacher | Assign Task | Remove Assign Task.
103 | Teacher | Create Exams | AI Generate: generate questions for selected topics or chapters from uploaded books.
104 | Teacher | Create Exams | Add a generation limit for uploading 3 class
105 | Teacher | Create Exams | Add Manual Exam Setting.
106 | Teacher | Exam Library | Remove Exam Library.
107 | Teacher | UI | Remove Poster.
108 | Teacher | Question Bank | Remove Question Bank.
109 | Teacher | Report / Analytics | Remove Report / Analytics.
110 | Teacher | Profile / Setting | Remove Profile / Setting.
111 | Teacher | UI | Remove the [U] icon/button.
113 | Student 3-A | Stories | Stories -> Research.
114 | Student 3-A | Stories | Add different stories.
115 | Student 3-A | Quiz | Remove Quiz.
116 | Student 3-A | My Work | Remove My Work.
117 | Student 3-A | Live Sessions | Remove Live Sessions.
118 | Student 3-A | Notifications | Remove 'My Trophies' from the Notification button.
119 | Student 3-A | UI | Reduce the size of the 'Classes line' poster.
120 | Student 3-A | UI | Align the cards properly.
121 | Student 3-A | Profile / Logout | Add Logout and Profile together.
122 | Student 7-A | Home | Keep only the highlighted features on Home: Activities, Tutor and Exams.
123 | Student 7-A | Home | Remove items from Home that do not work.
124 | Student 7-A | Subjects | Remove Subjects.
125 | Student 7-A | Activities | Testing required.
126 | Student 7-A | AI Chatbot | Big issue: no vision input - also manage the databse properly for each school
127 | Student 7-A | AI Chatbot | No text input either.
128 | Student 7-A | AI Chatbot | Response is taking longer.
129 | Student 7-A | AI Chatbot | Check API hitting.
130 | Student 7-A | Exams | Created exams should be shown.
131 | Student 7-A | My Tasks | Remove My Tasks.
132 | Student 7-A | Study Notes | Remove Study Notes.
133 | Student 7-A | PYQ | Remove PYQ.
134 | Student 7-A | Daily Challenge | Remove Daily Challenge.
135 | Student 7-A | SI | Remove SI.
136 | Student 7-A | Badge | Remove Badge.
137 | Student 7-A | Report an Issue | Remove Report an Issue.
138 | UI | Sidebar | Remove the left sidebar.
139 | UI | Buttons | Place every button frequently, as noted in the UI review.
140 | UI | Profile / Setting / Streak | Place Profile, Setting and Streak together.
141 | UI | Emojis | Remove unnecessary emojis.
142 | Student 10 | Home | Home -> Exams -> Highlight the feature / Lab.
143 | Student 10 | Subjects | Remove Subjects.
144 | Student 10 | Concept Mapping | Remove or improve Concept Mapping.
145 | Student 10 | Science Lab | Remove the left sidebar.
146 | Student 10 | Science Lab | Match the font of virtual labs of physics , chemistry and biology lab font with the whole website.
147 | Student 10 | Science Lab | Match the colors with the whole website.
148 | Student 10 | Science Lab | Testing required.
149 | Student 10 | Science Lab | No scrolling on the Lab page.
150 | Student 10 | Board Pro | Remove Board Pro.
151 | Student 10 | Daily Challenge | Remove Daily Challenge.
152 | Student 10 | Exams | Show exams assigned by teachers.
153 | Student 10 | Tasks | Remove Tasks.
154 | Student 10 | Notes | Remove Notes.
155 | Student 10 | PYQ | PYQ.
156 | Student 10 | Pomodoro Timer | Remove Pomodoro Timer.
157 | Student 10 | Profile / Setting | Add Profile / Setting / Edit together.
158 | Student 10 | Report an Issue | Remove Report an Issue.

## Module Summary
Module | No. of Items | Added Notes Module | No. of New Items
Super Admin | 2 | Dashboard | 2
Dashboard | 10 | Live Sessions | 2
Schools | 1 | Timetable | 1
Schools present | 1 | Students | 1
Features | 1 | Assign Task | 1
Admin Details | 1 | Create Exams | 3
Enrollment | 1 | Exam Library | 1
Student Directory | 1 | UI | 4
Content Portal | 5 | Question Bank | 1
Error messages | 1 | Report / Analytics | 1
AI Console | 5 | Profile / Setting | 2
Support Tickets | 5 | Games | 1
Audit logs | 3 | Stories | 2
| 11 | Quiz | 1
UI | 7 | My Work | 1
Profile / Setting | 1 | Notifications | 1
Classes + Sections | 1 | Profile / Logout | 1
Students | 8 | Home | 3
Teachers | 5 | Subjects | 2
Labs | 2 | Activities | 1
Timetable | 5 | AI Chatbot | 4
General | 1 | Exams | 2
Content Library | 6 | My Tasks | 1
Lab Incharge | 1 | Study Notes | 1
Feature Toggle | 1 | PYQ | 2
School Branding | 1 | Daily Challenge | 2
Principal Report | 1 | SI | 1
Promotion Wizard | 1 | Badge | 1
Support Ticket | 3 | Report an Issue | 2
Settings | 1 | Sidebar | 1
Sidebar | 2 | Buttons | 1
Classes & Section | 1 | Profile / Setting / Streak | 1
|  | Emojis | 1
|  | Concept Mapping | 1
|  | Science Lab | 5
|  | Board Pro | 1
|  | Tasks | 1
|  | Notes | 1
|  | Pomodoro Timer | 1