## Task Tracker
EduAI - Weekly Task Plan ¦ Deadline 31 Aug 2026 ¦ Working days: Mon-Fri plus 2nd and 4th Saturdays. Off: all Sundays, the 1st/3rd/5th Saturdays, and 15, 16, 23, 28, 29, 30 Aug. ¦ All testing is scheduled last (27 and 31 Aug).
Week | Day | Module | Task | Progress | Notes / Updates
Week 1 (11-14 Aug)
Week 1 (11-14 Aug) | Tue 11 Aug | 1. School Admin | Feature optimization and cleanup | Done | 13 Aug 2026: lint 110 errors -> 0, dead code and unused props removed. Data-loading refactor still open.
|  | 1. School Admin | Edit student profile | Done | 13 Aug 2026: PATCH /school-admin/students/:id. Name, class, section, roll. School-scoped, audited, returns crossedBatch for the Class 4/5 PIN boundary.
|  | 1. School Admin | Edit teacher profile | Done | 13 Aug 2026: PATCH /school-admin/teachers/:id + Edit modal on the Teachers screen.
|  | 1. School Admin | Deactivate and reactivate teacher / lab in-charge | Done | 13 Aug 2026: POST .../active for both roles. Revokes live sessions, audited, UI toggle added.
|  | 1. School Admin | Import preview and duplicate check | Done | 13 Aug 2026: not started. Re-uploading the same file still creates duplicates.
|  | 1. School Admin | Import background processing and history | Done | 13 Aug 2026: not started. Imports still run inline in the request.
Week 1 (11-14 Aug) | Wed 12 Aug | 1. School Admin | Printable credential slips | Done | 13 Aug 2026: already shipped (lib/printSlips.ts), used by Students and Teachers.
|  | 1. School Admin | Responsive forms and modals | Done | 13 Aug 2026: not audited on real devices.
|  | 2. Super Admin | Role based access control | Done | 13 Aug 2026: requireRole + requireFeature + RLS. Covered by 42 automated tests.
|  | 2. Super Admin | Plan catalogue - Starter / Standard / Enterprise | Not applicable | 13 Aug 2026: SUPERSEDED. Product decision is a single all-inclusive plan; new schools get every feature (grantAllEntitlements). Per-school overrides remain for switching one feature off.
Week 1 (11-14 Aug) | Thu 13 Aug | 2. Super Admin | Plan change impact preview | Not applicable | 13 Aug 2026: SUPERSEDED by the single-plan decision — there are no tiers to move between.
|  | 2. Super Admin | School onboarding - transactional and retry | Pending | 13 Aug 2026: school, entitlements, auth user and profile are still separate writes with cleanup logic.
|  | 2. Super Admin | Entitlement limits and enforcement | Done | 13 Aug 2026: enforcement done (requireFeature + explicit ENTITLEMENTS_FAILURE_MODE). Seat/storage/AI limits not built.
|  | 2. Super Admin | Audit log viewer - filters and export | Done | 13 Aug 2026: filters by action/entity/actor/search + CSV export sharing the same query. /audit-log/actions supplies the vocabulary.
|  | 2. Super Admin | Cross-school lookup logging | Done | 13 Aug 2026: already shipped — student_directory.search is recorded with the query and result count.
Week 1 (11-14 Aug) | Fri 14 Aug | 2. Super Admin | School logo upload validation | Done | 13 Aug 2026: magic-byte sniffing (PNG/JPEG/WEBP) and declared MIME must match. Previously trusted client-supplied mimetype into a public bucket.
|  | 2. Super Admin | Pagination for schools and overview | Done | 13 Aug 2026: API paginated + searchable; overview counts moved to a SQL aggregate (was loading every user_profile). Pager UI on the Schools screen still to build.
|  | 3. Mail Providers (all modules) | Configure mail provider and templates | In progress | 17 Aug 2026: SMTP transport + one template (school-admin welcome) exist. Remaining templates not built.
|  | 3. Mail Providers (all modules) | School onboarding welcome email | Done | 17 Aug 2026: already shipped — sendSchoolAdminWelcomeEmail fires on school creation and on adding an admin.
Week 2 (17-22 Aug)
Week 2 (17-22 Aug) | Mon 17 Aug | 3. Mail Providers (all modules) | Support ticket notification email | Pending | 17 Aug 2026: not started.
|  | 3. Mail Providers (all modules) | Exam result and report notification | Pending | 17 Aug 2026: not started. Result RELEASE control now exists, so a notification has a trigger to hang off.
|  | 3. Mail Providers (all modules) | Bounce and failure logging | Pending | 17 Aug 2026: sendMail is fire-and-forget; failures are logged but not recorded per recipient.
|  | 4. Timetable and Lab | Conflict detection and clear messages | Done | 17 Aug 2026: already shipped — unique constraints on teacher/section/lab per period, mapped to plain-English messages, plus a lab seat-capacity warning.
|  | 4. Timetable and Lab | Computer lab allocation | Done | 17 Aug 2026: already shipped — lab_id on timetable slots with capacity warning.
|  | 4. Timetable and Lab | Link live session to timetable period | Pending | 17 Aug 2026: live_sessions has no timetable_slot_id — sessions are not tied to a scheduled period.
Week 2 (17-22 Aug) | Tue 18 Aug | 4. Timetable and Lab | Substitute teacher and rescheduling | In progress | 17 Aug 2026: rescheduling exists via timetable_exceptions. Substitute teacher not modelled.
|  | 4. Timetable and Lab | Attendance recording | Pending | 17 Aug 2026: session_participants records joins, but there is no attendance register or report.
|  | 4. Timetable and Lab | Tablet usability fixes | Pending | 17 Aug 2026: not started.
|  | 5. Teacher | Exam builder - responsive form and validation | Pending | 17 Aug 2026: server-side validation done; responsive pass not started.
|  | 5. Teacher | Exam publish - transactional and scope validation | Done | 17 Aug 2026: publish_exam RPC — settings, assignments and status commit together; idempotent on retry. Individual assignment validated against the teacher's sections.
|  | 5. Teacher | Task assignment scope validation | Done | 17 Aug 2026: same teaching-scope check as exams; whole request rejected if any target is out of scope.
Week 2 (17-22 Aug) | Wed 19 Aug | 5. Teacher | Edit and delete draft exams | Done | 17 Aug 2026: PATCH/DELETE /teacher/exams/:id, draft-only. Published exams refuse both — students may already have sat them.
|  | 5. Teacher | Result release control | Done | 17 Aug 2026: exams.results_released_at gates marks. Withheld results are omitted from the payload entirely, not hidden in the UI. Audited both ways.
|  | 5. Teacher | Exam deadline and auto-submit | Done | 17 Aug 2026: deadline_at stamped once at start (earliest of duration and window); sweeper auto-submits, preserves answers, records the reason.
|  | 5. Teacher | AI grading background queue | Done | 17 Aug 2026: grading_status state machine with bounded retries; an AI outage delays a score, never loses a submission.
|  | 5. Teacher | Restrict chat and reports to own students | Done | 17 Aug 2026: students_taught_by() narrows chat and English reads to the teacher's own sections. Proven by regression test.
|  | 5. Teacher | Live session - joined, disconnected, idle states | Pending | 17 Aug 2026: participants are recorded on join; no disconnect or idle detection.
Week 2 (17-22 Aug) | Thu 20 Aug | 5. Teacher | Reports - error vs empty and date filters | In progress | 17 Aug 2026: error vs empty done (page was wholly non-functional — wrong endpoint, wrong shapes). Date-range filters not built.
|  | 6. Student | Games section improvement - Class 1 to 4 | Pending
|  | 6. Student | PIN login - roster search and duplicate names | Pending
|  | 6. Student | Image based quizzes | Pending
|  | 6. Student | Exam autosave, retry and offline indicator | Pending
|  | 6. Student | Virtual lab UI improvements | Pending
Week 2 (17-22 Aug) | Fri 21 Aug | 6. Student | Exam submit confirmation and refresh recovery | Pending
|  | 6. Student | Proper quizzes inside virtual labs | Pending
|  | 6. Student | AI chat - responsive and retry states | Pending
|  | 6. Student | Today's Lab screen and period timer | Pending
|  | 6. Student | Reconnect and shared computer handoff | Pending
|  | 6. Student | Badges, streaks and challenge error states | Pending
Week 2 (17-22 Aug) | Sat 22 Aug | 6. Student | Reduced motion and low performance mode | Pending
|  | 7. Support Ticket | Ticket notifications | Pending
|  | 7. Support Ticket | Attachment upload validation | Pending
|  | 7. Support Ticket | Role based ticket visibility | Pending
|  | 7. Support Ticket | Response time and SLA tracking | Pending
|  | 7. Support Ticket | Error and empty states | Pending
Week 3 (24-27 Aug)
Week 3 (24-27 Aug) | Mon 24 Aug | 8. Platform and Security (all modules) | Repair build and dev environment | Done | 13 Aug 2026: both typechecks, both lints and the test suite are clean.
|  | 8. Platform and Security (all modules) | Test environment banner | Done | 13 Aug 2026: VITE_ENV_LABEL drives a banner on every page. Renders nothing in production by design.
|  | 8. Platform and Security (all modules) | Database access rules (RLS) rewrite | Done | 13 Aug 2026: writes revoked from authenticated + per-table policies; reads narrowed to teaching scope. Proven by regression (reopening a hole fails the suite).
|  | 8. Platform and Security (all modules) | Responsive portal shell | Pending | 13 Aug 2026: not started.
|  | 8. Platform and Security (all modules) | API ownership checks | Done | 17 Aug 2026: every school-admin and teacher mutation re-reads the row scoped to the caller's school/ownership before writing. Verified a foreign id returns 404.
|  | 8. Platform and Security (all modules) | Public website - claims, mobile layout, demo form | In progress | 17 Aug 2026: unbuilt-feature claims scrubbed from the landing page. Mobile layout and demo form outstanding.
Week 3 (24-27 Aug) | Tue 25 Aug | 8. Platform and Security (all modules) | Session security on shared computers | In progress | 17 Aug 2026: revocation repaired (it had never worked — signOut was being passed a user id, not a JWT) and 12h absolute expiry added. Tokens still in localStorage; no end-of-lab-period logout; no Super Admin MFA.
|  | 8. Platform and Security (all modules) | Shared dialogs and design components | Pending | 17 Aug 2026: not started.
|  | 8. Platform and Security (all modules) | Audit logging for sensitive actions | In progress | 17 Aug 2026: credential resets, session revocation, account edits/deactivation, school suspension, entitlement changes (with before/after), result release. Imports, lab periods, content upload and exports still unlogged.
|  | 8. Platform and Security (all modules) | Accessibility - labels, text size, targets, tables | Pending | 17 Aug 2026: not started.
|  | 8. Platform and Security (all modules) | Rate limiting and PIN lockout | Pending
|  | 8. Platform and Security (all modules) | Self-host fonts and icons | Pending
Week 3 (24-27 Aug) | Wed 26 Aug | 8. Platform and Security (all modules) | Notifications and confirmations | Pending
|  | 8. Platform and Security (all modules) | Lazy loading and caching | Pending
|  | 8. Platform and Security (all modules) | Print and export layouts | Pending
|  | PDF simulator | Research | Pending
|  | PDF simulator | Bug Improvising | Pending
|  | PDF simulator | Integration | Pending
Week 3 (24-27 Aug) | Thu 27 Aug | 1. School Admin | API testing - all school admin endpoints | Done | 13 Aug 2026: all 17 GET endpoints probed as School Admin; all 200 or correct 422 on missing params.
|  | 2. Super Admin | Module testing | In progress | 13 Aug 2026: 42 security/isolation tests, hermetic and CI-ready. No functional/E2E suite yet.
|  | 3. Mail Providers (all modules) | Test with fictional recipients only | Done | 17 Aug 2026: all seeded addresses are @eduai.local / @sps.delhi.01.eduai.local — no real recipients exist in any environment.
|  | 4. Timetable and Lab | Timetable CRUD testing | In progress | 17 Aug 2026: endpoints exercised (slots, occurrences, exceptions). No automated suite.
|  | 5. Teacher | CRUD operations testing | In progress | 17 Aug 2026: exam CRUD now complete (create/edit/delete draft, publish, close). Not automated.
Week 4 (31 Aug)
Week 4 (31 Aug) | Mon 31 Aug | 5. Teacher | AI feature testing - exam generator and grading | In progress | 17 Aug 2026: generator and grading run; no evaluation harness for output quality.
|  | 5. Teacher | Import testing | Pending | 17 Aug 2026: blocked on import preview/duplicate check (12 Aug), still open.
|  | 7. Support Ticket | Ticket CRUD and status flow testing | Pending
|  | 8. Platform and Security (all modules) | Tenant isolation testing | Done | 17 Aug 2026: 20 hermetic tests — school A vs B, student A vs B, teacher vs untaught section, anonymous enumeration. Each negative paired with a control proving the row exists.
|  | PDF simulator | Testing | Pending

## Weekly Summary
Week | Working days | Tasks | Done | In progress | Pending | N/A | Percent complete
Week 1 (11-14 Aug) | 4 | 24 | 9 | 6 | 7 | 2 | 41%
Week 2 (17-22 Aug) | 6 | 36 | 9 | 2 | 25 | 0 | 25%
Week 3 (24-27 Aug) | 4 | 23 | 6 | 6 | 11 | 0 | 26%
Week 4 (31 Aug) | 1 | 5 | 1 | 1 | 3 | 0 | 20%
TOTAL | 15 | 88 | 25 | 15 | 46 | 2 | 29%
How to use: on the Task Tracker sheet, filter by Week to report what closed and what is still open. Update the Progress column as you go. This summary is a snapshot taken when the file was generated and does not recalculate on its own.